## Application
Application for payment
Yellow cells are yours to fill in. Every other figure is calculated from the Schedule of values sheet. Example figures are fictional: replace them.
Project | Maple Street Clinic (fictional)
From (contractor or subcontractor) | Copperline Plumbing (fictional)
To (owner or general contractor) | Northgate Builders (fictional)
Contract or subcontract | Plumbing subcontract
Application number | 3
Period to | 2026-03-31
Retainage rate | 10%
Previous payments (total earned less retainage on the last application) | 65520
Summary
1. Original contract sum
2. Net change by approved change orders
3. Contract sum to date (1 + 2)
4. Completed and stored to date
5. Retainage (line 4 × rate, rounded to the cent)
6. Total earned less retainage (4 − 5)
7. Less previous payments
8. Current payment due (6 − 7)
9. Balance to finish, including retainage (3 − 6)
Check: work this period + stored this period − retainage held this period
Matches line 8 when the rate hasn't changed and previous payments equal the last application's line 6
Signed for the contractor or subcontractor
Name and title
Date
Approved for payment by
Amount approved
Date

## Schedule of values
Schedule of values
One line per part of the work. Enter this period's work and materials stored; carry 'From previous applications' from the last application's column G. Retainage per line is for reference: the Application sheet rounds once on the total, so the lines can differ from it by a cent.
Item | Description of work | Scheduled value | From previous applications | Work this period | Materials presently stored | Completed and stored to date (D + E + F) | % complete (G ÷ C) | Balance to finish (C − G) | Retainage (reference)
1 | Mobilization and bonds | 6000 | 6000 | 0 | 0
2 | Underground rough-in | 38000 | 38000 | 0 | 0
3 | Above-ground rough-in | 72000 | 28800 | 25200 | 0
4 | Fixtures, material | 46000 | 0 | 0 | 18400
5 | Fixture installation and trim | 40000 | 0 | 0 | 0
6 | Water heaters and equipment | 18000 | 0 | 0 | 0
7 | Testing, closeout and as-builts | 20000 | 0 | 0 | 0
Original contract
CO-01 | Added floor drains, approved change order (fictional) | 4850 | 0 | 2425 | 0
Approved change orders
Total
Check: no line billed past its scheduled value