# Request for Information

## Request

| RFI number |  |
| --- | --- |
| Date sent |  |
| Project |  |
| Project number |  |
| To (who answers under the contract) |  |
| From |  |
| Copies to |  |
| Subject |  |

## References

| Drawing sheet(s) and detail |  |
| --- | --- |
| Specification section(s) |  |
| Location, room or grid line |  |

## Question

| Question (one question) |  |
| --- | --- |
| Proposed solution |  |
| Cost impact (None / Possible / Yes) |  |
| Schedule impact (None / Possible / Yes) |  |
| Answer needed by, and what it holds up |  |
| Attachments |  |

## Response

| Answer |  |
| --- | --- |
| Answered by (name, firm) |  |
| Date answered |  |
| Attachments or revised sheets |  |
| Does the answer change cost or time? (If yes, give notice under your contract) |  |

An RFI answer does not change the contract by itself. If you believe it adds cost or time, give the notice your contract requires. Free from conflo.co.

Filled-in example. The job, companies, sheets and dates are made up.

# Request for Information

## Request

| RFI number | RFI 007 |
| --- | --- |
| Date sent | March 3 |
| Project | Alder Street Medical Office (fictional) |
| Project number | 2603 |
| To (who answers under the contract) | Architect of record |
| From | GC project manager, for the plumbing subcontractor |
| Copies to | Structural engineer, MEP engineer, plumbing subcontractor, owner's representative |
| Subject | Floor drain FD-3 conflicts with footing at grid B/2 |

## References

| Drawing sheet(s) and detail | P-101 (plumbing plan, level 1); S-101 (foundation plan); detail 3/S-501 (footing section) |
| --- | --- |
| Specification section(s) | 22 13 19 |
| Location, room or grid line | Mechanical room 108, grid B/2 |

## Question

| Question (one question) | P-101 locates floor drain FD-3 in mechanical room 108, 1'-0" east of grid B. Detail 3/S-501 shows the footing on grid B extending 1'-6" east of the grid, so the drain would sit in the footing. Can FD-3 move 18 inches east, to 2'-6" east of grid B? |
| --- | --- |
| Proposed solution | Move FD-3 18 inches east. Keep the floor sloped to the drain as shown on the architectural plan. No change to pipe sizes. |
| Cost impact (None / Possible / Yes) | None expected if FD-3 moves as proposed |
| Schedule impact (None / Possible / Yes) | Possible: the underground inspection is March 12 and the slab pour March 17 |
| Answer needed by, and what it holds up | March 10, for the underground inspection on March 12 |
| Attachments | Marked-up P-101 with the proposed location; photo of the layout at grid B/2 |

## Response

| Answer | Accepted. Relocate FD-3 to 2'-6" east of grid B as proposed. Maintain floor slope to drain per A-101. No other changes. |
| --- | --- |
| Answered by (name, firm) | Project architect, architect of record (fictional) |
| Date answered | March 6 |
| Attachments or revised sheets | None |
| Does the answer change cost or time? (If yes, give notice under your contract) | No |