## How to use
How to use this submittal log
1. Go through the specifications section by section. In each section's Part 1, find the Submittals article and add one row for each item it asks for.
2. Fill in the spec section and paragraph, the title, the type, who prepares it and who reviews it. Mark information-only items as Information.
3. For each Action item, enter the date the material is needed on site, the supplier's lead time and the review time your specifications allow.
4. Approve by (required on site minus lead time) and Submit by (approve by minus review time) fill in. Sort by Submit by to get your submittal schedule.
5. As each one moves, enter the date sent, the date returned and the review code, and keep Ball in court current. Days in review counts until it is returned.
6. A resubmittal keeps its number and takes the next revision (Rev 1, Rev 2). Add it as a new row so the history stays.
Dates are calendar days. If your specifications count review time in working days, convert it before you enter it.
Free from conflo.co. Check your contract and specifications for the submittals, review times and codes that apply to your job.

## Submittal log
Submittal log
Project |  |  | Rows 9–13 are a filled-in example on a made-up job. Delete them before you use the log. Shaded columns are formulas.
Project number
General contractor
Architect
Log updated
No. | Rev | Spec section | Spec paragraph | Title | Type | Prepared by (sub or supplier) | Reviewer | Action or information | Schedule activity it holds up | Required on site | Lead time (days) | Review time (days) | Approve by | Submit by | Date sent | Date returned | Days in review | Review code | Ball in court | Notes
001 | 0 | 03 30 00 | 1.3 | Concrete mix designs | Design data | Granite Ridge Concrete (fictional) | Structural engineer | Action | Pour footings | 2026-11-16 | 7 | 14 | [5 empty] | Not yet submitted | Subcontractor
002 | 0 | 22 13 19 | 1.3 | Floor drains and cleanouts | Product data | Bluefield Plumbing (fictional) | MEP engineer | Action | Underground plumbing rough-in | 2026-12-07 | 21 | 14 | [5 empty] | Not yet submitted | Subcontractor
003 | 0 | 26 24 16 | 1.3 | Panelboards | Shop drawings | Corner Post Electric (fictional) | MEP engineer | Action | Set electrical gear | 2027-02-15 | 70 | 14 | [5 empty] | Not yet submitted | Subcontractor | Long lead: release order on approval
004 | 0 | 08 11 13 | 1.2 | Hollow metal doors and frames | Shop drawings | Ridgeway Doors (fictional) | Architect | Action | Set frames, level 1 | 2027-03-01 | 42 | 14 | [5 empty] | Not yet submitted | Subcontractor
005 | 0 | 08 11 13 | 1.2 | Hollow metal doors and frames: recycled content | Certificates | Ridgeway Doors (fictional) | Architect | Information | [11 empty] | For the record; no approval needed
Formulas:
Days in review = IF([Date sent]="","",IF([Date returned]="",TODAY()-[Date sent],[Date returned]-[Date sent]))

## Review codes
Review codes
Use the codes your specifications name (usually Division 01, Submittal Procedures). These are common ones.
Code | What it means | Can the work proceed?
Approved (or No exceptions taken) | Meets the contract documents as submitted | Yes
Approved as noted (or Make corrections noted) | Acceptable with the reviewer's corrections | Yes, if the corrections are made; some specs want a corrected copy for the record
Revise and resubmit | Incomplete or does not comply; fix and send again | No, not until the resubmittal is approved
Rejected (or Not approved) | Does not meet the contract documents | No; submit a compliant product or detail
Received for information (or Receipt acknowledged) | An information-only submittal, filed without a compliance review | Not an approval; build to the contract documents