## Look-ahead
Three-week look-ahead schedule
Project |  | Harbor Lane Clinic (fictional example) |  |  | Rows 9–16 are a filled-in example on a made-up job: delete them before you use the sheet. Type the Monday of the coming week in C3; the date columns follow.
Week of (a Monday) |  | 2026-11-02 |  |  | Grey columns are last week (what happened). Green bars are planned work; red bars are critical-path work (Critical = Y). Shaded columns are formulas.
Prepared by |  | GC superintendent
Issued |  | 2026-10-30
[9 empty] | Last week (as built) | Week 1 | Week 2 | Week 3
Schedule ID | Activity | Area | Responsible company | Crew | Start | Finish | Work days | Critical (Y/N) |  |  |  |  | What must be ready (submittal, material, inspection, RFI, access) | Ready (Y/N) | Notes
3.1 | Footings, area A | Area A | Ridgeline Concrete (fictional) | 6 | 2026-10-26 | 2026-10-30 |  | Y |  |  |  |  | Done Oct 30 (as built) | Y
3.1 | Stem walls, area A | Area A | Ridgeline Concrete (fictional) | 6 | 2026-11-02 | 2026-11-06 |  | Y |  |  |  |  | Wall rebar on site; footing inspection passed | Y
3.2 | Under-slab plumbing rough-in | Area A | Copper Ridge Plumbing (fictional) | 3 | 2026-11-09 | 2026-11-11 |  | Y |  |  |  |  | Stem walls backfilled | N | Backfill needs the walls cured; confirm Nov 6
3.2 | Under-slab electrical conduit | Area A | Brightline Electric (fictional) | 2 | 2026-11-09 | 2026-11-11 |  | N |  |  |  |  | Conduit on site | Y
3.2 | Under-slab inspection (city) | Area A | City inspector |  | 2026-11-12 | 2026-11-12 |  | Y |  |  |  |  | Request the inspection the day before | N | Book on Nov 11
3.3 | Vapor retarder, rebar and slab pour | Area A | Ridgeline Concrete (fictional) | 6 | 2026-11-13 | 2026-11-17 |  | Y |  |  |  |  | Inspection passed; pump truck booked; pre-pour meeting | N | Pour Nov 17 if dry
4.1 | Steel delivery and erection, area A | Area A | Northgate Steel (fictional) | 4 | 2026-11-18 | 2026-11-20 |  | Y |  |  |  |  | Shop drawings approved; anchor bolts surveyed; crane permit | N | Delivery confirmed for Nov 18
1.5 | Submit door hardware submittal |  | Keystone Doors (fictional) |  | 2026-11-02 | 2026-11-06 |  | N |  |  |  |  | Hardware schedule from the architect | Y | Off site: 10-week lead time after approval

## Holidays
Non-working days (holidays, planned shutdowns) | Type one date per row. Work days on the look-ahead skip these and weekends.

## How to use
How to use this three-week look-ahead
1. Type the Monday of the coming week in C3 on the Look-ahead sheet. The 20 date columns are last week (grey) and the next three weeks.
2. Take each activity from your project schedule that starts, continues or finishes in the next three weeks, and put its schedule ID in column A.
3. Break it into pieces a foreman can plan a crew around: an area, a floor, a pour. Keep each line to five work days or fewer.
4. Give every line a responsible company, a crew size, a start and a finish. Work days count Monday to Friday and skip the dates on the Holidays sheet.
5. Mark critical-path work Y in 'Critical'; its bars turn red.
6. For every line, write what must be ready before it can start (an approved submittal, material on site, a passed inspection, an answered RFI, access), and mark Ready Y only when it is.
7. Keep last week's lines, with what actually happened, so the meeting starts from the as-built.
8. Issue it before the weekly subcontractor meeting, walk it line by line, and update it every week.
Rows 9-16 on the Look-ahead sheet are a filled-in example on a made-up job (Harbor Lane Clinic). Delete them before you use the sheet.
From conflo.co/templates/three-week-look-ahead-template. Free to use and change.